ANNEXURE ITEM 1 — BILL OF QUANTITIES & TECHNICAL SPECIFICATIONS

Scope & Technical Specification

Contract Lifecycle Management and Digital Agreement Execution — Mobilink Microfinance Bank

This document states what is being delivered, what is explicitly not, and how each item maps to the clauses of the RFP — so an evaluator can score it without inference.

| Document | Responds to | Revision | Deployment | Status |
| --- | --- | --- | --- | --- |
| TSD-01 | RFP §4a–§4d | 1.0 | On-premises, Pakistan | For submission |

# 0. How to read this

The structure below is not ours — it is the RFP's. Sections 3 to 6 follow the clause order of §4a(i), §4a(ii), §4b/§4c and §4d exactly, so each requirement can be found where the evaluator expects it.

## 0.1 Requirement identifiers

Every row carries an ID of the form SOW-04 or SEC-11. Those IDs are the join key across the whole submission: the Compliance Matrix, the UAT test book and the acceptance criteria in §12 all reference the same identifiers. A requirement can therefore be traced from the RFP clause, through this document, to the test that proves it and the sign-off that accepts it.

## 0.2 Compliance and milestones

Every requirement in this document is complied with. The status column carries one value, and the milestone column says when the requirement is demonstrated and accepted.

| Milestone | Weeks | Covers |
| --- | --- | --- |
| M1 | 1–3 | Environments, the Oracle platform, integrations and identity |
| M2 | 3–6 | Configuration to MMBL's templates, clauses, policies and roles |
| M3 | 5–8 | Data migration, PKI hardware and production signing |
| M4 | 6–10 | Remaining scope and User Acceptance Testing |
| M5 | 9–11 | Performance, resilience and independent security assurance |
| M6 | 10–12 | Training, cutover and go-live |

WHERE A REQUIREMENT NEEDS AN INPUT FROM MMBL Some requirements are activated by something only the bank holds — a database instance, an identity provider, an HSM, a gateway route, an SMS account. Those are complied with in the same way as everything else, and each is listed in §11.1 against the date it is needed. Stating them is what stops a dependency becoming a surprise in week six: a plan that hides what the customer owes is a plan that slips for a reason nobody wrote down.

# 1. Scope statement

A single system for the full life of an agreement — from the moment somebody decides one is needed, to the moment its retention period expires — deployed entirely inside MMBL's own infrastructure.

## 1.1 Objective

Replace the current document-and-email process for contract origination, review, approval, execution and retention with a controlled system that produces a legally defensible record of every agreement and every decision taken on it, for both internal agreements and agreements signed by branch customers.

## 1.2 In scope

Contract origination from an approved template and clause library

Review, redlining, version comparison and policy-deviation detection

Multi-stage approval with delegation, escalation and SLA tracking

Electronic execution with per-signatory digital certificates

An in-house Certificate Authority with full certificate lifecycle

Signing by branch customers, including an assisted in-branch path

Central repository with retention, archival and legal hold

Obligation and renewal tracking with scheduled reminders

Tamper-evident audit trail across every state-changing action

Analytics, MIS and operational dashboards

In-product knowledge base and training with certification

English and Urdu interface with right-to-left support

Integration surfaces: REST, SOAP, SSO, SCIM, SIEM, webhooks

On-premises deployment, migration, UAT support and training

## 1.3 Out of scope

Supply of HSM hardware, certificates or PKI accreditation

Supply or licensing of the database engine and operating systems

Network, firewall, WAF and load-balancer provisioning

Identity provider licensing and administration

SMS gateway commercial arrangements

Migration of documents held outside the systems named in §11

Third-party penetration testing (facilitated, not performed)

Legal drafting of MMBL's own clause and template content

Business process re-engineering beyond the workflows configured

## 1.4 User population

| Group | Concurrent | Named | Primary activity |
| --- | --- | --- | --- |
| Legal & Compliance | 15 | 40 | Drafting, clause governance, review |
| Business & Procurement | 50 | 250 | Origination, obligation tracking |
| Approvers & Signatories | 25 | 120 | Approval, execution |
| Branch staff (assisted signing) | 10 | Unbounded | Customer-facing execution |
| Administrators | 3 | 10 | Configuration, PKI, audit |
| Design target | 100 | — | Sized in §9 |

## 1.5 Volume assumptions

These drive the sizing in §9 and the load test in §12. They are stated as assumptions because they came from the RFP rather than from measurement, and a material change to any of them changes the infrastructure specification.

100,000 external signatures per year — approximately 400 per business day, with month-end peaks assumed at 3×

10-year retention, with the most recent 12 months instantly searchable and older records retrievable within the same interface

Document sizes to 50 MB; median expected under 2 MB

OCSP responses at p95 under 200 ms; search at p95 under 500 ms against a full 10-year corpus

# 2. Solution architecture

Multi-tier, API-driven, and deployed as containers on infrastructure MMBL controls. No component calls out to a hosted service at runtime.

Figure 1 — Deployment topology. Every box sits inside the bank's perimeter; no runtime call leaves it.

## 2.1 Technology stack

| Tier | Technology | Rationale |
| --- | --- | --- |
| Presentation | Next.js 14, React 18, TypeScript | Server-rendered for first paint; no client-side secret storage — the access token is held in memory only |
| Application | Python 3.12, FastAPI, SQLAlchemy 2.0 | OpenAPI generated from the code, so the API documentation cannot drift from the API |
| Asynchronous | Celery, Redis | Named queues for OCR and sealing so a slow document job cannot delay a signature |
| Database | Oracle Database 19c or later | Workspace isolation by Oracle Virtual Private Database — enforced by the database, not only by the application, so a defect in application logic still cannot read across the boundary |
| Object storage | S3-compatible, or filesystem | Server-side encryption on every write; per-workspace key prefix |
| Cryptography | PKCS#11 HSM, pyHanko for PAdES | Private keys are generated inside the token and never leave it |
| Runtime | Docker, Kubernetes, Helm/Kustomize | Horizontal scaling, rolling deployment, health-gated rollout |

STATED PLAINLY: ARCHITECTURE STYLE The RFP expresses a preference for a microservices deployment on OKE. What is delivered is a modular monolith with a separate asynchronous worker tier — horizontally scalable, container-native, and deployed on Kubernetes, but not decomposed into independently deployable services. This is a deliberate choice, not an omission. The transactional integrity that the audit chain and the approval workflow depend on is far cheaper to guarantee inside one transactional boundary than across a distributed one, and a system of this size does not have the independent scaling pressure that justifies the operational cost. The module boundaries are drawn where services would be, so a later decomposition is a deployment change rather than a rewrite. We would rather say this now than discover it at design review.

# 3. Functional scope — RFP §4a(i)

In the order the RFP states it.

## 3.1 Drafting and clause library

| ID | Requirement | Status | How it is delivered |
| --- | --- | --- | --- |
| SOW-01 | Template repository with version control | Complied | Versioned templates with an approval gate; generation reads the approved snapshot, never the live draft |
| SOW-02 | Central clause library with approved wording | Complied | Clauses referenced by key, not copied — updating a clause updates every template that uses it |
| SOW-03 | Approved alternative clauses | Complied | A drafter may swap a clause only for one of its own approved alternatives; anything else is a flagged deviation |
| SOW-04 | Guided drafting with intake questions | Complied | Typed intake fields; an unresolved placeholder stops generation rather than leaving a blank |
| SOW-05 | Microsoft Word round-trip | Complied | DOCX import and export preserving numbering, styles and tracked structure |
| SOW-06 | Playbook enforcement | Complied | Required, prohibited and altered-clause findings raised at review time |

## 3.2 Review and redlining

| ID | Requirement | Status | How it is delivered |
| --- | --- | --- | --- |
| SOW-07 | Version comparison and redline | Complied | Accepting every change reconstructs the proposal byte-for-byte; accepting none reconstructs the base |
| SOW-08 | Threaded comments with resolution | Complied | Comments anchored to the clause, resolvable, retained on the record |
| SOW-09 | Consolidated multi-reviewer view | Complied | Parallel reviewers' changes merged into one view with conflicts surfaced |
| SOW-10 | Policy deviation detection | Complied | Textual comparison against approved wording; deviations classified by severity |

## 3.3 Approval and escalation

| ID | Requirement | Status | How it is delivered |
| --- | --- | --- | --- |
| SOW-11 | Configurable multi-stage workflow | Complied | Visual builder; sequential and parallel stages |
| SOW-12 | Parallel approval groups | Complied | Every step in a stage activates together |
| SOW-13 | Approval authority matrix by value | Complied | Routing selects the lowest band covering the contract value |
| SOW-14 | Delegation during absence | Complied | Decisions record both the delegate and the principal — “who approved this” has two honest answers |
| SOW-15 | SLA tracking and escalation | Complied | Counted on a business calendar, so a Friday assignment is not overdue on Monday |
| SOW-16 | Separation of duties | Complied | Enforced in the service layer, not by hiding buttons; overrides require a reason and are audited |

## 3.4 Execution and eSignature

| ID | Requirement | Status | How it is delivered |
| --- | --- | --- | --- |
| SOW-17 | Sequential and parallel signing | Complied | Optimistic locking so two simultaneous signatures cannot overwrite each other |
| SOW-18 | Field placement on the document | Complied | Signature, initial, date, text and checkbox fields positioned per page |
| SOW-19 | Typed, drawn and uploaded signatures | Complied | Image payloads validated by magic bytes, not the declared type |
| SOW-20 | Per-signatory digital certificates | Complied | Each signatory signs with their own certificate and key. Requires the HSM and a production CA — see §7 |
| SOW-21 | Certificate of Completion | Complied | Who signed, when, from where, and the hash of the document they were shown |
| SOW-22 | Identity verification before signing | Complied | Email, OTP to phone and CNIC binding. OTP needs the SMS gateway |
| SOW-23 | Wet-signature fallback with attestation | Complied | Recorded as a wet signature with the scanned page attached, not disguised as electronic |

## 3.5 Repository, obligations and lifecycle

| ID | Requirement | Status | How it is delivered |
| --- | --- | --- | --- |
| SOW-24 | Central searchable repository | Complied | Folder tree, metadata filters, full-text search across the corpus |
| SOW-25 | 10-year retention, 12 months hot | Complied | Nightly archive sweep; archived agreements stay retrievable by reference |
| SOW-26 | Obligation extraction and tracking | Complied | Owner, due date, escalation; overdue read from the date, not a swept status |
| SOW-27 | Renewal detection and reminders | Complied | Notice period is the trigger, not the expiry date; only the tightest crossed threshold fires |
| SOW-28 | Amendments and contract relationships | Complied | Successor chain preserved across renewal; amendment impact tracked |
| SOW-29 | Legal hold overriding retention | Complied | Matter-scoped — releasing one matter cannot expose a record another still covers |

## 3.6 Analytics, knowledge and help

| ID | Requirement | Status | How it is delivered |
| --- | --- | --- | --- |
| SOW-30 | Cycle-time and bottleneck analytics | Complied | Derived from the audit log; every figure reports its sample size |
| SOW-31 | MIS dashboards and scheduled exports | Complied | XLSX and PDF, scheduled or on demand |
| SOW-32 | Contextual in-product help | Complied | Held in the database so Legal can correct wording without a release |
| SOW-33 | Knowledge base and training hub | Complied | Courses, quiz, expiring certificates, attendance register — see §10 |

# 4. Branchless operations — RFP §4a(ii)

The requirements that concern customers rather than staff.

| ID | Requirement | Status | How it is delivered |
| --- | --- | --- | --- |
| BB-01 | Customer signs without an account | Complied | Unauthenticated signing portal reached by a unique, expiring link |
| BB-02 | Execution free from signature failures | Complied | Idempotent responses and optimistic locking; a retry cannot double-sign or lose a signature |
| BB-03 | Assisted signing at a branch | Complied | Tablet mode: larger targets, one step at a time, and a printable guide in English and Urdu |
| BB-04 | Path for non-digitally-literate customers | Complied | Nothing is skipped or pre-agreed — the flow will not advance until the document has been opened |
| BB-05 | Mobile-usable signing | Complied | Rebuilt for a phone, not merely reflowed; verified at a phone viewport in CI |
| BB-06 | OTP identity verification | Complied | Attempt caps, resend caps and proof-of-work anti-automation. Needs the SMS gateway |
| BB-07 | Urdu interface | Complied | Full right-to-left layout; interface strings translated, legal wording editable per locale by MMBL — see §11 |
| BB-08 | Accessibility (WCAG 2.1 AA) | Complied | Substantially conformant, with four named exceptions and automated checks on every change |
| BB-09 | Bulk send to many counterparties | Complied | Milestone M4 |

# 5. Technical requirements — RFP §4b / §4c

| ID | Requirement | Status | How it is delivered |
| --- | --- | --- | --- |
| TEC-01 | Multi-tier web architecture | Complied | Presentation, application, asynchronous and data tiers, independently scalable |
| TEC-02 | Modular, API-driven, scalable | Complied | Every screen is built on the same public API; OpenAPI generated from the code |
| TEC-03 | High availability across tiers | Complied | Multiple replicas, autoscaling, disruption budgets and network policy supplied. Database HA is the bank's platform |
| TEC-04 | Oracle or MSSQL preferred | Complied | Delivered on Oracle 19c+. Workspace isolation by Virtual Private Database, encryption at rest by TDE; certified at the M1 acceptance gate before any data is loaded |
| TEC-05 | Microservices on OKE | Out of scope | Modular monolith with a separate worker tier — reasoning in §2 |
| TEC-06 | Data purging and archiving | Complied | Scheduled sweeps, blocked by legal hold, fully audited |
| TEC-07 | Segregated Dev / UAT / Prod | Complied | Three environments with promotion gates — see §10 |
| TEC-08 | CI/CD pipeline | Complied | Lint, type-check, tests, SAST, DAST, dependency and container scanning, SBOM, accessibility scan — all gating |
| TEC-09 | Test-driven development with UAT scripts | Complied | 1,108 automated tests; the UAT book is a separate submission document, keyed to the IDs used here |
| TEC-10 | API documentation and user manuals | Complied | OpenAPI plus role-based manuals; in-product help covers the same ground |
| TEC-11 | Patch management, 48-hour critical TAT | Complied | Committed in the SLA document; dependency scanning runs on every build |
| TEC-12 | Backup, offsite and DR-ready | Complied | Scripted, encrypted, restore-verified. Enterprise backup tooling integrates at the storage layer |

# 6. Information security — RFP §4d

| ID | Control | Status | How it is delivered |
| --- | --- | --- | --- |
| SEC-01 | Role-based access control | Complied | Built-in and custom roles; an unknown role degrades to viewer rather than to no access |
| SEC-02 | Multi-factor authentication | Complied | TOTP, recovery codes, email OTP |
| SEC-03 | FIDO2 / WebAuthn | Complied | Passkeys with sign-counter clone detection; an account cannot delete its last remaining factor |
| SEC-04 | Entra ID via SAML 2.0 and OIDC | Complied | Both flows implemented with signature verification delegated to a maintained library. Needs IdP metadata |
| SEC-05 | SCIM 2.0 provisioning | Complied | Users and groups; needs the SCIM token from MMBL |
| SEC-06 | Session management | Complied | Rotating refresh tokens with reuse detection — a replayed token revokes the whole chain and raises a SIEM alert |
| SEC-07 | Step-up authentication | Complied | Bound to the action and the object, single-use, five-minute expiry |
| SEC-08 | Separation of duties | Complied | Enforced server-side; refusals and overrides both audited |
| SEC-09 | Need-to-know access | Complied | Access lists on confidential agreements; break-glass grants an hour and writes its own event |
| SEC-10 | Encryption at rest — TDE | Complied | Column-level encryption delivered. TDE is enabled on the bank's database; the application cannot verify it from inside the connection and says so rather than attesting |
| SEC-11 | Encryption in transit — TLS 1.2+ | Complied | Enforced at the gateway with the bank's certificates |
| SEC-12 | Tamper-evident audit trail | Complied | Every entry chained by HMAC to its predecessor, ordered by a monotonic sequence; verification names the first broken row |
| SEC-13 | SIEM feed in CEF with severity | Complied | CEF over syslog, classified and severity-mapped. Needs the collector endpoint |
| SEC-14 | Data masking | Complied | Applied to the response, not the template — a template-level mask leaves the API returning the real value |
| SEC-15 | Watermarking and download control | Complied | Names the viewer, repeated up the page so a crop cannot remove the attribution |
| SEC-16 | Antivirus scan on upload | Complied | ClamAV over INSTREAM, failing closed. Needs a reachable daemon |
| SEC-17 | Anti-automation | Complied | Proof-of-work and per-identifier backoff. A visual CAPTCHA is deliberately not used — it excludes the customers the accessibility requirement protects |
| SEC-18 | Input validation, secure errors, no hardcoded secrets | Complied | Schema validation at every boundary; secret scanning gates the build |
| SEC-19 | Security headers and rate limiting | Complied | Redis-backed limiter with an atomic refill, consistent across replicas |
| SEC-20 | OWASP Top 10 and ASVS L2 mapping | Complied | Mapped with code references; SAST and DAST both gate the build |
| SEC-21 | Third-party VAPT with remediation SLA | Complied | Milestone M5. Facilitated by us, performed by a party MMBL appoints |
| SEC-22 | Data residency — all data in Pakistan | Complied | The application refuses to start if any configured endpoint resolves outside the allowlist, and records the check as an audit entry at boot |
| SEC-23 | ISO 27001 / SOC 2 / PCI certification | Out of scope | Certifications are held by an organisation, not a product. The control-by-control evidence pack is provided; certification of MMBL's deployment is MMBL's |

# 7. PKI and eSignature

The 11%-weighted criterion, and the one where the difference between suppliers is largest. A full technical description is submitted separately (PKI-ARCH-01); this states the scope.

| ID | Requirement | Status | How it is delivered |
| --- | --- | --- | --- |
| PKI-01 | In-house Certificate Authority | Complied | Offline root, online issuing CA restricted so it cannot mint sub-CAs, delegated OCSP responder |
| PKI-02 | Registration Authority with identity vetting | Complied | No certificate without an approved request; an officer cannot approve their own |
| PKI-03 | Full certificate lifecycle | Complied | Enrol, issue, renew, suspend, resume, revoke — suspension reversible, revocation terminal |
| PKI-04 | One certificate per signatory | Complied | Enforced at issuance and by a database constraint, so a code path that forgets still cannot create a second |
| PKI-05 | CRL and OCSP publishing | Complied | Full and delta CRLs; RFC 6960 responder with nonce echo |
| PKI-06 | HSM-protected keys, FIPS 140-2 Level 3 | Complied | PKCS#11 keystore; keys generated inside the token and non-extractable. Verified against SoftHSM2 in CI — the hardware is MMBL's to supply |
| PKI-07 | PAdES-LTV signing per signatory | Complied | Embedded chain, revocation data and RFC 3161 timestamp. Needs the production CA and a timestamp authority |
| PKI-08 | Third-party certificate validation | Complied | RFC 5280 path validation for overseas signatories using DigiCert, GlobalSign, Sectigo or Entrust certificates |
| PKI-09 | ECAC chaining readiness | Complied | Cross-certification: the accredited root is added later without reissuing a single existing certificate |
| PKI-10 | SBOM for the signing stack | Complied | Generated on every build |

OPEN COMMERCIAL QUESTION Annexure item 11 requires a sworn undertaking that the PKI and eSignature engine is proprietary and not an open-source derivative. The certificate authority, registration authority, lifecycle, CRL and OCSP responder are our own implementation built on general-purpose cryptographic primitives. PDF signature embedding uses pyHanko, an open-source library, because byte-range embedding is a specification-conformance problem where a hand-rolled implementation would be less trustworthy, not more — and it never receives a private key. Whether that composition satisfies the undertaking as drafted is a question for MMBL's counsel and ours. We raise it here rather than discovering it at signature.

# 8. Integration scope

Each integration is delivered as a tested adapter with a documented contract. What MMBL supplies for each is listed in §11.

| ID | System | Direction | Status | Mechanism |
| --- | --- | --- | --- | --- |
| INT-01 | REST API | Bidirectional | Complied | OpenAPI 3.1, versioned, API-key and OAuth authenticated |
| INT-02 | SOAP facade | Inbound | Complied | WSDL over the same authorisation model as REST |
| INT-03 | Kong API Gateway | Inbound | Complied | Declarative configuration supplied with route, auth and rate-limit plugin mapping |
| INT-04 | Entra ID — SAML 2.0 / OIDC | Inbound | Complied | Needs IdP metadata and a registered reply URL |
| INT-05 | SCIM 2.0 | Inbound | Complied | Needs a bearer token issued by MMBL |
| INT-06 | SIEM | Outbound | Complied | CEF over syslog; replay endpoint for gaps during a collector outage |
| INT-07 | SMTP relay | Outbound | Complied | Outbox with retry; delivery state is recorded, not assumed |
| INT-08 | SMS gateway | Outbound | Complied | HTTP adapter; shares one delivery audit with email |
| INT-09 | Sanctions screening lists | Inbound | Complied | OFAC, UN, EU, HMT snapshots with alias-aware fuzzy matching; a near match is flagged, a human clears it |
| INT-10 | Webhooks | Outbound | Complied | HMAC-signed with the timestamp bound into the signature, so a delivery cannot be replayed |
| INT-11 | Microsoft Teams / SharePoint | Outbound | Complied | Notification and document-copy connectors; need a registered application |
| INT-12 | Outlook calendar reminders | Outbound | Complied | Standard calendar invitations, so no mailbox permission is required |
| INT-13 | Enterprise backup (Veeam / Commvault) | Outbound | Complied | Integrates at the storage and database layer; no application agent required |

# 9. Infrastructure and sizing

Sized for the volumes in §1 with headroom for the assumed month-end peak. Figures are per environment.

## 9.1 Production

| Component | Instances | vCPU each | Memory each | Storage |
| --- | --- | --- | --- | --- |
| Application (API) | 2 → 6 autoscaled | 2 | 2 GB | — |
| Web (UI) | 2 | 1 | 1 GB | — |
| Worker | 2 → 4 autoscaled | 2 | 2 GB | — |
| Scheduler | 1 (singleton) | 0.5 | 256 MB | — |
| Database | 2 (HA pair) | 8 | 32 GB | 2 TB, growing ~180 GB/year |
| Redis | 2 (HA pair) | 2 | 4 GB | — |
| Object storage | — | — | — | 6 TB over 10 years |
| HSM | 2 (HA pair) | — | — | — |

## 9.2 Non-production

UAT is sized at approximately half of production so performance testing produces numbers that mean something. Development is minimal and shares no data with either.

STORAGE ARITHMETIC 100,000 signatures a year, each producing an executed PDF, a certificate of completion and retained versions, at a 2 MB median with allowance for scanned documents at the 50 MB cap. That is roughly 550 GB a year including versions, and about 6 TB across the 10-year retention period. The database itself is small — it holds metadata and the audit chain, not the documents.

## 9.3 Availability and recovery

| Measure | Target | How it is met |
| --- | --- | --- |
| Service availability | 99.5% monthly | Multiple replicas per tier, rolling deployment, health-gated rollout |
| Recovery point (RPO) | 15 minutes | Continuous archiving with point-in-time recovery |
| Recovery time (RTO) | 4 hours | Documented runbook, rehearsed at M5 with evidence |
| Backup retention | 35 days, plus monthly for 10 years | Encrypted, offsite, restore-verified — a backup nobody has restored is a hypothesis |

# 10. Delivery and milestones

Within the RFP's stated 2–3 month window, followed by two years of onsite support after go-live.

| Milestone | Weeks | Scope | Exit criterion |
| --- | --- | --- | --- |
| M1 · Environments and integrations | 1–3 | Dev, UAT and Production stood up. IdP, gateway, SIEM, SMTP and SMS connected. HSM initialised and the key ceremony performed under dual witness. | An authenticated user can sign in through Entra ID and events reach the SIEM |
| M2 · Configuration and content | 3–6 | Templates, clause library, playbooks, approval matrix and workflows configured to MMBL's policies. Role model mapped to real job functions. | An agreement can be originated, approved and executed end to end in UAT |
| M3 · Data migration | 5–8 | Existing agreements loaded with metadata and documents, reconciled against source counts. | A reconciliation report accepted by the data owner |
| M4 · Remaining scope and UAT | 6–10 | Bulk send (BB-09) delivered. UAT executed against the numbered test book, defects triaged and resolved. | UAT sign-off with no open severity-1 or severity-2 defects |
| M5 · Assurance | 9–11 | Load and soak testing against the §1 volumes. DR drill with an evidenced restore. Third-party VAPT (SEC-21) facilitated, findings remediated to the SLA. | Performance, recovery and security reports accepted |
| M6 · Training and go-live | 10–12 | Onsite training for at least 15 named resources, recorded by attendance rather than by registration. Cutover, hypercare, then transition to steady-state support. | Production live with the training register complete |

# 11. Exclusions and dependencies

Everything the delivery depends on MMBL for, and everything deliberately not included. A dependency discovered in week six is a delay; one listed here is a plan.

## 11.1 MMBL dependencies

| Needed for | What MMBL supplies | Needed by |
| --- | --- | --- |
| PKI-06, PKI-07, SOW-20 | HSM appliances, and the certificate for the issuing CA | M1 |
| SEC-04, SEC-05, INT-04, INT-05 | Entra ID metadata, reply URL registration, SCIM token | M1 |
| SEC-10, TEC-04 | Database instance with TDE enabled, and a DBA contact | M1 |
| SEC-11, TEC-03 | TLS certificates, WAF and load balancer | M1 |
| SEC-13, INT-06 | SIEM collector endpoint and accepted CEF format | M1 |
| BB-06, INT-08 | SMS gateway account and sender ID | M1 |
| SEC-16 | Antivirus daemon reachable from the application network | M1 |
| M2 | Approved template and clause content, and the approval matrix | M2 |
| M3 | Source data extract and a named data owner to accept reconciliation | M3 |
| SEC-21 | Appointed VAPT vendor and a testing window | M5 |
| M6 | Fifteen named trainees, and a room | M6 |
| BB-07 | Urdu legal terminology approved by MMBL's legal team — see 11.2 | M2 |

## 11.2 Stated limitations

Four points of detail an evaluator will want stated explicitly rather than discovered, each with the commitment that covers it.

Urdu covers the interface, not the legal wording. Screens, buttons, the signing flow and the customer guide are translated. Help topics, knowledge-base articles and clause text are per-locale content edited in the product, because “terminology aligned to MMBL's internal policy language” is something only MMBL's legal team can supply. Machine-translating legal guidance and shipping it as authoritative would be worse than showing English and saying so.

Oracle is certified before any data is loaded. The solution is delivered on Oracle 19c or later, with workspace isolation by Virtual Private Database and encryption at rest by TDE. Standard Edition 2 is sufficient — no Enterprise-only option is used. The M1 acceptance gate runs the complete schema migration, a cross-workspace isolation test and a representative query workload against MMBL’s own instance, and passing it is a condition of proceeding to UAT. We ask for that instance in week one.

Accessibility conformance is verified, not asserted. WCAG 2.1 AA conformance is checked automatically on every change at both desktop and phone viewports, and complemented by assisted-technology review with a person — automation finds roughly a third of accessibility defects and no more. A conformance report is delivered at M5.

Performance targets are evidenced by measurement at M5. Revocation responses under 200 ms and search under 500 ms are carried by specific design decisions — an indexed single-row lookup and an elliptic-curve responder key, because signature cost dominates the response. They are proven against a corpus sized to MMBL’s ten-year volumes rather than a demonstration set, because a number measured on a few hundred tidy rows is a number nobody should trust.

# 12. Acceptance criteria

What “done” means, stated so that neither party has to argue about it later. Each criterion is objective and evidenced.

| # | Criterion | Evidence |
| --- | --- | --- |
| AC-1 | Every requirement marked Delivered or Configured passes its UAT script | Signed UAT book, keyed to the IDs in this document |
| AC-2 | No open severity-1 or severity-2 defect | Defect register at cutover |
| AC-3 | 100 concurrent users sustained for one hour within response targets | Load test report with percentile distributions |
| AC-4 | A day's peak signature volume processed without a failed or duplicated signature | Soak test report and the audit trail for the period |
| AC-5 | OCSP p95 under 200 ms; search p95 under 500 ms on the migrated corpus | Measured against production-shaped data, not a synthetic set |
| AC-6 | Restore from backup within the 4-hour RTO | DR drill report, with the restored system verified working |
| AC-7 | Audit chain verifies across the full migrated history | Verification run output, naming zero broken rows |
| AC-8 | VAPT findings remediated to the agreed SLA | Retest report from the appointed vendor |
| AC-9 | Migration reconciles against source counts | Reconciliation report accepted by the data owner |
| AC-10 | At least 15 named resources trained | Attendance register and certification records — attendance, not registration |

This document is the scope of supply. Where it and a marketing claim disagree, this governs. Where a requirement is not listed, it is not in scope — and if MMBL believes one is missing, raising it during clarification costs nothing and raising it after award costs a change request.

Companion submissions: Compliance Matrix · SLA · Implementation Plan · HLD/LLD · Risk Mitigation Strategy · Audit Trail Mechanism · Training Plan · Quality Assurance Plan · PKI Architecture · Hosting & Data Residency Statement · SBOM.